## Sheet1
Report of Sprint 1
Sprint Planning | 2014/10/1-2014/10/15
Sprint implementations days | 15 | days |  | Effort | Remainning
trend calculated based on last | 9 | days |  | 20 | 18 | 18 | 17 | 16.6 | 9 | 8.5 | 6.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task name | Story ID or description/Issue ID | Responsible | Status | Estimated | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Create Main Camera | As a user I want the camera to follow the PC./#13 | Iván Álvarez | Done | 7h | 7 | 7 | 7 | 7 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Make zoom | Extra Issue/#16 | Iván Álvarez | Done | 1h | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logic for the selection in the menu | As a user I want to have an initial screen to select play/#8 | Joshúa García | Done | 8h | 8 | 8 | 8 | 7.6 | 3 | 2.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design for Main Screen | As a user I want to have an initial screen to select play/#17 | Oscar Conejo | Done | 4h | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
completed hours
|  |  |  | 2 | 0 | 1 | 0.4 | 7.6 | 0.5 | 2 | 5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Burndown Chart
Evaluación individual -Iván Álvarez:Ha acabado las tareas en una semana. Aparte de lo que tenía que hacer de que la cámara persiga al personaje, también ha hecho una extra del zoom. -Joshúa García:Ha acabado las tareas en una semana. También vino a ayudar a los integradores, gracias a él, la integración se ha completado con éxito. -Oscar Conejo: Ha acabado las tareas en una semana, el diseño sobre el menú que ha hecho les ha gustado a los compañeros. -Tian Lan: Ha asegurada que las issues de los compañeros son finalizadas, y se ha reunido con los demás integradores para hacer la integración.